Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 11 September 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Metro Ticket Generating System in ServiceNow |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Architecture & Schema | USN-1 | Create custom table u_metro_station_details and configure field u_station_name with master station entries. | 3 | High | Core Team |
| Sprint-1 | Security & Governance | USN-2 | Verify out-of-the-box Table ACLs on u_metro_station_details to secure direct database tampering while allowing public portal read. | 2 | Med | Core Team |
| Sprint-1 | Catalog Item Setup | USN-3 | Build 'Book A Metro Ticket' catalog item under 'Services' category with variables for Source, Destination, Journey Type and Passenger Count. | 5 | High | Core Team |
| Sprint-2 | Dynamic Fare Automation | USN-4 | Develop onChange Catalog Client Script to calculate single/return journey fares based on route sys_ids and passenger counts. | 5 | High | Core Team |
| Sprint-2 | Conditional UI Policy | USN-5 | Configure Catalog UI Policy to dynamically display "Enter payment mode" input when "Others" is selected under Mode of Payment. | 2 | Med | Core Team |
| Sprint-2 | Client Form Validation | USN-6 | Enforce mandatory field constraints on Source, Destination, and Passenger Count to eliminate null or partial catalog submissions. | 3 | High | Core Team |
| Sprint-3 | QR Generator Client Script | USN-7 | Create onSubmit Catalog Client Script to construct dynamic QR endpoint URL using the record unique identifier (SysID). | 5 | High | Core Team |
| Sprint-3 | Service Portal QR Widget | USN-8 | Develop custom portal widget metro_qr_widget and trigger interactive preview modal via spModal.open before confirmation. | 5 | High | Core Team |
| Sprint-3 | Service Portal Routing | USN-9 | Test and verify complete booking workflow directly from Service Portal (/sp) across mobile and desktop viewport layouts. | 3 | Med | Core Team |
| Sprint-4 | Fulfillment Automation | USN-10 | Configure Flow Designer workflow to map catalog variables into sc_req_item and generate fulfillment tasks (sc_task). | 5 | High | Core Team |
| Sprint-4 | End-to-End QA & Testing | USN-11 | Execute comprehensive testing for fare accuracy, QR scannability at turnstiles, and edge route error handling using Execution Details. | 3 | High | Core Team |
| Sprint-4 | Documentation & Demo | USN-12 | Compile technical blueprint, setup manual for PDI replication, video demo walkthrough, and project presentation assets. | 4 | Med | Core Team |

Project Tracker, Velocity & Burndown Chart:

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 5 Days | 18 Aug 2026 | 22 Aug 2026 | 10 | 22 Aug 2026 |
| Sprint-2 | 10 | 5 Days | 25 Aug 2026 | 29 Aug 2026 | 10 | 29 Aug 2026 |
| Sprint-3 | 13 | 5 Days | 01 Sep 2026 | 05 Sep 2026 | 13 | 05 Sep 2026 |
| Sprint-4 | 12 | 5 Days | 08 Sep 2026 | 12 Sep 2026 | 12 | 12 Sep 2026 |
| Total Project | 45 Points | 20 Days (4 Wks) | 18 Aug 2026 | 12 Sep 2026 | 45 Points | 12 Sep 2026 |

Velocity Formulation

Total Story Points Completed = 10 + 10 + 13 + 12 = 45 Points

Number of Sprints = 4

Team Velocity = Total Story Points/Number of Sprints = 45/4 = 11.25 Story Points per Sprint

Average Velocity (AV) per Day = Total Story Points/Total Days = 45/20 = 2.25Story Points / Day

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.